## Test Case Writing
Product Name |  | Daraz | TC Start Date | 2023-06-23 | TC Execution Start Date | 2023-06-25 |  |  |  |  | TEST CASE
Module Name |  | Registration | TC End Date | 2023-06-24 | TC Execution End Date | 2023-06-26 |  |  |  |  | PASS | 54
Epic |  |  | Test Case Developed By | Ishmam Faruki | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 59
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'daraz' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
9 |  |  |  | Checking 'exclusive offers and promotions via SMS' checkbox is not enabled by default | Should not be enabled by default | Not found as per expectation | N/A | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox | exclusive offers and promotions Checkbox |  | Failed
10 |  | Functional Testing |  | Entering a pre-registered mobile number | User should not get a verification code for registration | User did not get any verification code | Phone Number: 8801938907943 | 1. Go to URL 2. Click on SIGNUP Button 3. Click on Reister here 4. Enter a used phone number 5. Click on "SEND" from SMS Verification Code Field |  |  | Passed
11 |  |  |  | Entering a new/unused mobile number | User should get a verification code for registration | User got a verification code for further registration process | Phone Number: 8801521428784 | 1. Repeat 1-3 from TC-001 2. Enter a new phone number 3. Click on "SEND" from SMS Verification Code Field |  |  | Passed
12 |  |  |  | Entering an invalid mobile number | User should get an error popup | User got an error popup | Phone Number: 0171226$3B7 | 1. Repeat 1-3 from TC-001 2. Enter an invalid phone number 3. Click on "SEND" from SMS Verification Code Field |  |  | Passed
13 |  |  |  | Entering no mobile number | User should get a warning | User got a warning saying "You can't leave this empty" | Phone Number: | 1. Repeat 1-3 from TC-001 2. Enter no phone number 3. Click on "SEND" from SMS Verification Code Field |  |  | Passed
14 |  |  |  | Entering a valid number preceding with single '+' | User should get a verification code for registration | User got a verification code for further registration process | Phone Number: +8801521428784 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number, preceding with single '+' 3. Click on "SEND" from SMS Verification Code Field |  |  | Passed
15 |  |  |  | Entering a valid number preceding with multiple '+' | User should not get a verification code for registration | User got a verification code for further registration process | Phone Number: +++8801521428784 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number, preceding with multiple '+' 3. Click on "SEND" from SMS Verification Code Field | Bug No. 1 in Phone Number Field |  | Failed
16 |  |  |  | Enter the correct received code within 5 minutes | User should be verified for further registration | User verification code is correct | Code: 371579 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field |  |  | Passed
17 |  |  |  | Enter a wrong code | User should not be verified for further registration | User get a warning about wrong code | Code: 494949 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter a wrong code in verification code field |  |  | Passed
18 |  |  |  | Enter the correct received code after 5 minutes | User should not be verified for further registration and must get another new code to continue | User get a warning about wrong code | Code: 371579 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field |  |  | Passed
19 |  |  |  | Entering less than 6 characters consists of only letters | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: asdqz | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter less than 6 characters consists of only letters |  |  | Passed
20 |  |  |  | Entering less than 6 characters consists of only numbers | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: 12345 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter less than 6 characters consists of only numbers |  |  | Passed
21 |  |  |  | Entering less than 6 characters consists of both letters & numbers at least once | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: 123A45 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter less than 6 characters consists of both numbers & letters |  |  | Passed
22 |  |  |  | Entering more than 5 and less than 51 characters consists of only letters | User should get a warning | User got a warning saying "Password should contain both alphabetic and numeric characters" | Password: AbCDeFG | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 5 and less than 51 characters consists of only letters |  |  | Passed
23 |  |  |  | Entering more than 5 and less than 51 characters consists of only numbers | User should get a warning | User got a warning saying "Password should contain both alphabetic and numeric characters" | Password: 12345678 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 5 and less than 51 characters consists of only numbers |  |  | Passed
24 |  |  |  | Entering more than 5 and less than 51 characters consists of both letters & numbers at least once | User should not get any warning and should be able to enter other informations | User was able to carry on registration process without any warnings | Password: 1234A678 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 5 and less than 51 characters consists of both letters & numbers at least once |  |  | Passed
25 |  |  |  | Entering more than 50 characters consists of only letters | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: AAAAAAAADAAAAAAAAAAAAAABAAAAAAAAAAAAAABAAAAAAAAAAAAAAbAAAAAAAAAAAAAAAAAAAAAAAAAAAAAaAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAa | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 50 characters consists of only letters |  |  | Passed
26 |  |  |  | Entering more than 50 characters consists of only numbers | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: 215151664484966161616464464648646465656546546556156165156654848419191654654576576161616516516546546465765464 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 50 characters consists of only numbers |  |  | Passed
27 |  |  |  | Entering more than 50 characters consists of both numbers & letters | User should get a warning - "The length of Password should be 6-50 characters" | User got the warning | Password: AswqffjasdjasdasdasdaasgaQ54848419191654654576576161616516516546546465765464 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in verification code field 5. Enter more than 50 characters consists of both numbers & letters |  |  | Passed
28 |  |  |  | Click on Password hide button | Password should be hidden and in place of hide button now an unhide button should arrive | Password got hidden and unhide button took place | Password: ****** | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Click on password hide button |  |  | Passed
29 |  |  |  | Click on Password unhide button | Password should be visible again and in place of unhide button now a hide button should arrive again | Password got visible and hide button arrived again | Password: 12345A | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Click on password unhide button |  |  | Passed
30 |  |  |  | Enter any date after present day | User should get a warning about wrong birthday | User got the warning | Date: May-27-2023 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter any date after present day and fillup month, day, and year accordingly in the birthday field |  |  | Passed
31 |  |  |  | Enter any valid date | User should be able to register with this valid date | User can register with a valid birthday | Date: May-26-2023 | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter any valid date and fillup month, day, and year accordingly in the birthday field |  |  | Passed
32 |  |  |  | Enter an invalid date | User should not be able to register with this invalid date | User can register with a invalid birthday | Date: 29-Feb-2019, 30-feb-2020, 31-feb-2020, 31-Apr-1995 etc. | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter any invalid date and fillup month, day, and year accordingly in the birthday field | Bug No. 2 in Birhtday Field |  | Failed
33 |  |  |  | Choose a gender between Male & Female | User should be able to choose between male & female gender | User can choose either Male or Female | Gender: Male | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender: Male or Female |  |  | Passed
34 |  |  |  | Gender field doesn’t have any third gender/other option | User should be able to choose third gender/other option | User can't choose because third gender option is not added yet |  | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender | Bug No. 3 in Gender Field |  | Failed
35 |  |  |  | Entering less than 2 character | The user should get a warning - "The Name length should be 2-50 characters" | User got the warning | Full Name: A | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender 8. Enter Full Name |  |  | Passed
36 |  |  |  | Entering more than 50 character | The user should get a warning - "The Name length should be 2-50 characters" | User got the warning | Full Name: Sultan Suleman Ikhtiar Uddin Muhammad Bin Bakhtiyar Khilji | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender 8. Enter Full Name |  |  | Passed
37 |  |  |  | Entering more than 1 and less than 51 characters consists of atleast one number | User should get a warning saying "Number is not allowed in Full Name" | User did not get any warning and could register with a name consists of number | Full Name: 12A | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender 8. Enter Full Name | Bug No. 4 in Full Name Field |  | Failed
38 |  |  |  | Checking "Tick Button" for receiving notifications | Tick Button should be checked if previously unchecked | Tick button can be checked (if previously unchecked) | Tick Button: Check | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender 8. Enter Full Name 9. Click on tick button to check |  |  | Passed
39 |  |  |  | Unchecking "Tick Button" for not receiving notifications | Tick Button should be unchecked if previously checked | Tick button can be unchecked (if previously checked) | Tick Button: Unheck | 1. Repeat 1-3 from TC-001 2. Enter valid phone number 3. Click on "SEND" from SMS Verification Code Field 4. Enter the received code in the verification code field 5. Enter a valid password 6. Enter a valid date 7. Choose a gender 8. Enter Full Name 9. Click on tick button to uncheck |  |  | Passed
40 |  |  |  | Click on signup with facebook to check if it's possible to signup with an existing facebook account | User should be able to signup with an existing facebook account | User can register with an existing facebook account |  | 1. Repeat 1-3 from TC-001 2. Click on Signup with facebook button |  |  | Passed
41 |  |  |  | Click on signup with google to check if it's possible to signup with an existing google account | User should be able to signup with an existing google account | User can register with an existing google account |  | 1. Repeat 1-3 from TC-001 2. Click on Signup with google button |  |  | Passed
42 |  |  |  | Check Remove All(X) Button | User should be able to remove the entire phone number field after clicking "remove all(x)" button | User can remove the entire phone number field after clicking "remove all(x)" button |  | 1. Repeat 1-3 from TC-001 2. Enter a phone number 3. Click on (X) beside the field |  |  | Passed
43 |  |  |  | Check Remove All(X) Button | User should be able to remove the entire password field after clicking "remove all(x)" button | User can remove the entire password field after clicking "remove all(x)" button |  | 1. Repeat 1-3 from TC-001 2. Enter a password 3. Click on (X) beside the field |  |  | Passed
44 |  |  |  | Check Remove All(X) Button | User should be able to remove the entire full name field after clicking "remove all(x)" button | User can remove the entire full name field after clicking "remove all(x)" button |  | 1. Repeat 1-3 from TC-001 2. Enter a full name 3. Click on (X) beside the field |  |  | Passed
45
46
47
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 |  |  |  | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field |  |  |  | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field |  |  |  | Passed
51 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A |  |  |  | Passed
52 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | john@8888 |  |  |  | Passed
53 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 |  |  |  | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: janev4141@gmail.com Password: jane@2222 |  |  |  | Passed
55 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A |  |  |  | Passed
56 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A |  |  |  | Passed
57 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A |  |  |  | Passed
58 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A |  |  |  | Passed
59 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 |  |  |  | Passed
60 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: janev4141@gmail.com Password: jane@2222 |  |  |  | Passed
61 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 |  |  |  | Passed
62 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found as per expectation | N/A |  |  |  | Passed
|  |  | Improvement Scopes | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
Place 'Whats this?' below 'Remember Me'
Place 'Forgot your password' link below Password field
Negative test

## Test Case Report
Test Case Report
Project Name | BD Shop
Module Name | Sign Up and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 54 | PASS
Written By | Ishmam Faruki |  |  |  |  | 5 | FAIL
Executed By | Ishmam Faruki |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 54 | 5 | 0 | 0 | 59
Grand Total | 54 | 5 | 0 | 0 | 59
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 09 | # SL 15 | # SL 32 | # SL 34 | # SL 37
Issue: Checking 'exclusive offers and promotions via SMS' checkbox is not enabled by default | Issue: Entering a valid number preceding with multiple '+' | Issue: Entering an invalid date in birthday filed | Issue: Gender field doesn’t have any third gender/other option | Issue: full name accepts numbers
Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on the Register button at the right corner 3. Fill in all the fields 4. check that exclusive offers and promotions via SMS is enabled by default | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on the Register button at the right corner 3. Fill the phone number with a valid number preceding with multiple '+' | 1. Goto the URL https://member.daraz.com.bd/user/register2. Click on the Register button at the right corner 3. Fill invalid date i.e: 31 february 1961 | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on the Register button at the right corner 3. Fill all the imformation 4. click on gender | 1. Goto the URL https://member.daraz.com.bd/user/register 2. Click on the Register button at the right corner 3. Fill all the fields 4. enter a full name with a number
Env: Production | Env: Production | Env: Production | Env: Production | Env: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P3 | Severity: P2 | Severity: P1 | Severity: P2 | Severity: P2
Screenshot: Checkbox error | Screenshot: Phone number error | Screenshot: invalid date error | Screenshot: Gender Error | Screenshot: Full Name Error
Responsible QA: Ishmam Faruki | Responsible QA: Ishmam Faruki | Responsible QA: Ishmam Faruki | Responsible QA: Ishmam Faruki | Responsible QA: Ishmam Faruki

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (59/59)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/59)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (54/59)*100 = 91.53
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/59)*100 = 8.47
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/59)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A